## Sheet1
Section | Element | Description | Status
Opening | UI | Menu Scene | Done
| UI | Exit Function | Done
| UI | Intro Scene | Done
Intro | Audio | Narration | Done
| Audio | Bang of door | Done
| Audio | VO of owner | Done
| Audio | Ambient music | Done
| Transitions | Menu to Instructions | Done
| Transitions | Menu to Intro | Done
| Transitions | Intro to Chapter 1 | Done!!
Main | Enviro | Glasses on shelves | Done
|  | Other kitchen wares on shelves | Done
|  | Bricks for smashing vases | Done
|  | Make all drawers work | Done
|  | Handle puzzle locked drawer | Done
|  | Handle key locked drawer | Done
|  | Make taps | Done
|  | Place taps | Done
|  | Add FRAGILE box to clue vase smashing | Done
|  | Door handle on inside of top door (non functional) | Done
| Inventory | Camera rendering to plane | Done
|  | Highlights for inventory objects | Done
|  | Spots for inventory objects | Done
|  | Code for selecting inventory objects | Nearly done - return positioning is off
|  | Code for storing inventory objects | Done
| Puzzles | Wine bottle placement in slots | Done
|  | Bricks smashing vases | Done
|  | Searching sack for key | Done
|  | Make ladder necessary to teleport into dumbwaiter | Done
|  | Make colour changes work for kegs | Done
|  | Make tap insertion work for kegs | Done
| Gameplay | Make teleport targets/rotations | Abandoned - not practical with this layout
|  | Allow teleporting with full hands | Done
| UI | Inventory viewing | Done
| Clues | Keg colour clue on barrel at bottom of stairs | Done
|  | Keg colour clue inside dumbwaiter | Done
|  | Keg colour clue in drawer | Done
End | Audio | Win music | Done
| Enviro | Animation of middle cask opening | Done
| Gameplay | Trigger Stay Tuned panel | Done
| UI | Credits scene | Done